## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: | Web Development
INTERN NAME: | Faraj Momin
DOCUMENT NAME: | TEST PLAN
CREATED ON: | 2024-07-23
Purpose of Document
A Test Plan is a detailed document that describes the test strategy, objectives, schedule, estimation, deliverables, and resources required to perform testing for a software product.
Test Plan helps us determine the effort needed to validate the quality of the application under test.
The test plan serves as a blueprint to conduct software testing activities as a defined process, which is minutely monitored and controlled by the test manager
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments are added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled

## TEST PLAN
TEST PLAN
PROJECT NAME | College Finder
PROJECT ID | IP -4039
INTERN NAME | Faraj Momin
PROJECT MANAGER | Harshada Topale
INTRODUCTION
This test plan outlines the strategies, processes, workflows, and methodologies used to ensure the quality and reliability of the Indian engineering college search web application. The primary objective is to identify and address defects, verify functionality, and validate that the application meets its specified requirements. Testing will include unit, integration, system, and user acceptance levels. Both automated and manual testing will be utilized: automated tests for repetitive tasks and regression, and manual tests for exploratory and usability testing. The process will follow a structured workflow: identify test cases, execute tests, report defects, and retest. Adopting Agile testing practices with continuous integration and delivery (CI/CD) will ensure early issue detection and rapid iterations. Version control systems and collaborative tools will facilitate effective communication and coordination among team members throughout the testing process.
SCOPE
IN SCOPE (Defines the features, functional or non-functional requirements of the software that will be tested)
Functional Requirements: User registration and login College search and filtering functionality College profile pages User profile management Application form submission Non-Functional Requirements: Performance and load testing Security testing Usability testing Compatibility testing across various browsers and devices
OUT SCOPE (Defines the features, functional or non-functional requirements of the software that will NOT be tested)
This test plan excludes testing third-party APIs, data from external sources, and any features or functionalities related to future updates or planned enhancements that are not currently implemented. Additionally, testing for accessibility compliance beyond basic usability will not be covered.
QUALITY OBJECTIVE
(Mention the overall objective that you plan to achieve without your testing)
1.Ensure reliable performance of the web application. 2. Verify all features function as intended. 3. Confirm the application meets functional and non-functional requirements. 4.Ensure the application is user-friendly and intuitive. 5. Validate compatibility across different devices and browsers. 6. Identify and resolve any defects or issues. 7. Deliver a secure and efficient platform for users.
ROLES AND RESPONSIBILITIES
(Detail description of the Roles and responsibilities of different team members)
1. Project Manager: Oversee testing, manage resources, ensure deadlines. 2. Test Lead: Develop test strategy, supervise test execution. 3. Test Engineer: Create and execute tests, document defects. 4. Developer: Fix defects, support testing. 5. Business Analyst: Clarify requirements, review test cases. 6. QA Specialist: Conduct quality reviews, improve processes.
TEST METHODOLOGY
OVERVIEW (Mention the reason of adopting a particular test methodology for the project)
1. Unit Testing: Verify individual functions and modules of the web application. 2. Integration Testing: Check interactions between different components 3.Functional Testing: Ensure all features meet the specified requirements. 4.Usability Testing: Assess the user interface and overall user experience. 5.Performance Testing: Evaluate the application’s responsiveness and load handling. 6.Security Testing: Identify and address potential vulnerabilities. 7.Regression Testing: Confirm that new changes do not affect existing functionality. 8.User Acceptance Testing (UAT): Validate the application meets user needs and expectations.
TEST LEVELS (Define the Types of Testing to be executed on the Application Under Test (AUT))
1.Unit Testing 2. Integration Testing 3. System Testing 4. User Acceptance Testing (UAT)
BUG TRIAGE (Define resolution of each bug, prioritize bugs and determine a schedule for all “To Be Fixed Bugs’)
1. Identification: Report and log all bugs. 2. Prioritization: Categorize bugs as Critical, Major, Minor, or Enhancement. 3. Resolution: Assign bugs to team members for fixes. 4. Scheduling: Set deadlines for bug fixes based on priority.
TEST COMPLETENESS (Define the criteria that will deem your testing complete)
1. Coverage: Achieve 100% test coverage for all features and functionalities. 2. Execution: Execute all manual and automated test cases. 3. Bug Status: Resolve all critical and major bugs, with minor bugs noted for future releases.
TEST DELIVERABLES
(Mention all the Test Artifacts that will be delivered during different phases of the testing lifecycle)
1. Test Plan 2. Test Cases 3.Test Scripts 4. Test Data 5. Test Reports 6. Bug Reports 7. Test Summary Report
RESOURCE AND ENVIRONMENT NEEDS
TESTING TOOLS
1. Hardware: Testing servers and computers 2. Software: Web browsers, OS, and database systems 3. Network: Internet and internal network access 4. Testing Tools: Bug tracking, test management, and automation tools
TEST ENVIRONMENT (Minimum hardware requirements that will be used to test the Application)
Processor: Minimum Intel i5 or equivalent RAM: At least 8 GB Storage: Minimum 100 GB free disk space Network: Stable internet connection Browser: Latest versions of Chrome, Firefox, Edge
ADDITIONAL COMMENTS
None
TEST PLAN
ITEMS TO TEST | TEST DESCRIPTION | TEST START DATE | TEST END DATE | RESPONSIBLE PERSON | STATUS | COMMENTS
College Search Functionality | Ensure that the search feature returns accurate results based on user input and filters. | 2024-07-17 | 2024-07-18 | Project Developer | PASSED | None
College Detail Page | Check that each college’s detail page displays correct and complete information. | 2024-07-18 | 2024-07-18 | Project Developer | PASSED | None
Responsive Design | Test that the application’s UI is functional and visually consistent across different devices and screen sizes. | 2024-07-19 | 2024-07-20 | Project Developer | PASSED | None
Database Integration | Validate that data is correctly retrieved from and stored in the database | 2024-07-20 | 2024-07-21 | Project Developer | PASSED | None
Error Handling and Validation | Confirm that the application handles errors gracefully and provides clear validation messages for incorrect input. | 2024-07-21 | 2024-07-22 | Project Developer | PASSED | None
Deployment and Environment Configuration | Verify that the application deploys correctly to the production environment and that all environment-specific configurations are correctly set up and functioning. | 2024-07-22 | 2024-07-23 | Project Developer | PASSED | None
Note on C17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To determine scope, you must – > Precise customer requirement > Project Budget > Product Specification > Skills & talent of your test team
Note on C24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The objective of the testing is finding as many software defects as possible; ensure that the software under test is bug free before release. To define the test objectives, you should do 2 following steps: > List all the software features (functionality, performance, GUI…) which may need to test. > Define the target or the goal of the test based on above features
Note on C40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: A Testing Type is a standard test procedure that gives an expected test outcome. all Testing Types are aimed at achieving one common goal “Early detection of all the defects before releasing the product to the customer. There are tons of Testing Types for testing software product. Your team cannot have enough efforts to handle all kind of testing. As Test Manager, you must set priority of the Testing Types > Which Testing Types should be focused for web application testing? > Which Testing Types should be ignored for saving cost? The commonly used testing types are: 1. Unit Testing 2. API Testing 3. Integration Testing 4. System Testing 5. Install/Uninstall Testing 6. Agile Testing You need to decide based on your project scope, time and cost the testing type(s) required for your project
Note on C48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Test Criteria is a standard or rule on which a test procedure or test judgment can be based. There’re 2 types of test criteria as following Suspension Criteria Specify the critical suspension criteria for a test. If the suspension criteria are met during testing, the active test cycle will be suspended until the criteria are resolved. Exit Criteria It specifies the criteria that denote a successful completion of a test phase. The exit criteria are the targeted results of the test and are necessary before proceeding to the next phase of development. Example: 95% of all critical test cases must pass.