## Project Schedule
|  | IAC Internship Progra 2024 - Web Development Project Schedule |  |  |  |  | PROJECT NAME | College Finder
[7 empty] | PROJECT MANAGER | Harshada Topale
|  | PROJECT START DATE | 2024-06-21 |  |  |  | PROJECT START DATE | 2024-06-21
|  | Project End Date | 2024-07-27 |  |  |  | PROJECT END DATE | 2024-07-27
|  | Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f |  |  |  |  | OVERALL PROGRESS | Completed
Sr No | Week/ Duration/ Sprint/ Phase | Activities | Task | Sub Task | Assigned to | Start Date | End Date | Actual End Date | Hours required | Status | Progress
1 | Week 1 | Project Initiation |  |  |  | 2024-06-21 | 2024-06-26 | 2024-06-26 | 8 Hrs | Completed | Done
1.1 |  |  | Define Project Goals and Objectives | Identify the primary goals of the College Finder Web Application. | Project Developer | 2024-06-21 | 2024-06-22 | 2024-06-22 | 2 Hrs | Completed | Done
1.2 |  |  | Conduct Feasibility Study | Assess the technical, operational, and financial feasibility of the project. | Project Developer | 2024-06-22 | 2024-06-23 | 2024-06-23 | 2hrs | Completed | Done
1.3 |  |  | Develop Project Charter | Create a document outlining the project's objectives, scope, stakeholders, and roles. | Project Developer | 2024-06-23 | 2024-06-24 | 2024-06-24 | 2.5 hrs | Completed | Done
1.4 |  |  | Develop SRS DOCUMENT |  | Project Developer | 2024-06-24 | 2024-06-26 | 2024-06-26 | 1.5 hrs | Completed | Done
2 | Week 2 | Project Planning |  |  |  | 2024-06-28 | 2024-07-03 | 2024-07-03 | 9 Hrs | Completed
2.1 |  |  | Define Project Scope | Create a Work Breakdown Structure (WBS) to outline tasks and subtasks. | Project Developer | 2024-06-28 | 2024-06-29 | 2024-06-29 | 1 Hrs | Completed | Done
2.1 |  |  | Develop Project Schedule | Create a timeline for the project using Gantt charts or similar tools. | Project Developer | 2024-06-29 | 2024-06-30 | 2024-06-30 | 2.5 Hrs | Completed | Done
2.3 |  |  | Risk Management Planning | Create a risk management plan and update it regularly. | Project Developer | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2.5 Hrs | Completed | Done
2.4 |  |  | Determine the resources required |  | Project Developer | 2024-07-02 | 2024-07-03 | 2024-07-03 | 3 Hrs | Completed | Done
3 | Week 3 | Project Building (Frontend) |  |  |  | 2024-07-05 | 2024-07-14 | 2024-07-14 | 12.5 Hrs | Completed | Done
3.1 |  |  | Writing HTML Code | Work on Structure of website | Project developer | 2024-07-05 | 2024-07-07 | 2024-07-07 | 3.5 Hrs | Completed | Done
3.2 |  |  | Writing CSS Code | Work on designing | Project developer | 2024-07-08 | 2024-07-11 | 2024-07-11 | 4 Hrs | Completed | Done
3.3 |  |  | Writing Javascript Code | Work on Functionality | Project developer | 2024-07-12 | 2024-07-14 | 2024-07-14 | 5 Hrs | Completed | Done
4 | Week 4 | Project Building(Backend) |  |  |  | 2024-07-15 | 2024-07-18 | 2024-07-18 | 9 hrs | Completed | Done
4.1 |  |  | Finding college information on internet | Information with another details | Project Developer | 2024-07-15 | 2024-07-17 | 2024-07-17 | 7 hrs | Completed | Done
4.2 |  |  | Integrating with javascript | Integrating with javascript | Project Developer | 2024-07-18 | 2024-07-18 | 2024-07-18 | 2 hrs | Completed | Done
5 | Week 5 | Project Testing |  |  |  | 2024-07-19 | 2024-07-20 | 2024-07-20 | 5 hrs | Completed | Done
5.1 |  |  | Set Up Testing Environment | Configure the testing environment to mirror the production setup. | Project Developer | 2024-07-19 | 2024-07-19 | 2024-07-19 | 2 hrs | Completed | Done
5.2 |  |  | Perform Integration Testing | Test interactions between integrated components to ensure they work together as expected. | Project Developer | 2024-07-20 | 2024-07-20 | 2024-07-20 | 3 hrs | Completed | Done
6 | Week 5 | Project Deployment |  |  |  | 2024-07-21 | 2024-07-23 | 2024-07-23 | 5 hrs | Completed | Done
6.1 |  |  | Deploy Application to Production |  | Project Developer | 2024-07-21 | 2024-07-22 | 2024-07-22 | 2.5 hrs | Completed | Done
6.2 |  |  | Perform Post-Deployment Testing |  | Project Developer | 2024-07-23 | 2024-07-23 | 2024-07-23 | 1 hrs | Completed | Done
6.3 |  |  | Deploy on Github Pages |  | Project Developer | 2024-07-23 | 2024-07-23 | 2024-07-23 | 1.5 hrs | Completed | Done
7 | Week 6 | Documentation & Submission |  |  |  | 2027-07-24 | 2024-07-27 | 2024-07-27 | 5.10 hrs | Completed | Done
7.1 |  |  | Create a project Report |  | Project Developer | 2027-07-24 | 2027-07-25 | 2027-07-25 | 5 hrs | Completed | Done
7.2 |  |  | Create a short 5 min video |  | Project Developer | 2024-07-26 | 2024-07-26 | 2024-07-26 | 10 min | Completed | Done
7.3 |  |  | Submit Project |  | Project Developer | 2024-07-27 | 2024-07-27 | 2024-07-27 |  | Completed | Done
Note on G7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Nirbhey Singh Pahwa - I was thinking if we should add an actual start date column as well? Reply: Or, let's call this one as planned start date and the next one as start date. The same can be done for End date. Because, writing 'actual' feels as if we've missed some deadline of some sorts so can be avoided. You can have this in the DM Goals template for now, let me add this to the next version of this template, i.e., Goals [Template v0.5] Thank you